## TestCases
Test Case ID | Feature Tested | Description | Precondition | Test Steps | Expected Result | Actual Result | Status | Comments
1 | Recruitment Workflow Execution | Validates full recruitment lifecycle: candidate addition, rejection, shortlisting, interview handling, and job offer issuance. | User has access to Recruitment module | 1. Access Recruitment 2. Add candidate 3. Perform reject/shortlist 4. Initiate interview, mark result 5. Offer job | All operations execute correctly with backend responses and data updates | Shortlist/reject fails with 500 error; others untested due to failure | Fail | Severe API error halts workflow; major usability issue.
2 | Performance Tracker CRUD | Ensures Create, Read, Update, Delete functions for performance trackers behave as expected across sessions. | Access to Performance module | 1. Access Performance 2. Create tracker 3. Edit tracker 4. Delete tracker | Trackers persist without refresh, reflect changes across sessions | All operations work as intended with live updates | Pass | CRUD fully functional; real-time updates work.
3 | Buzz Media Sharing | Checks upload and display of media files in Buzz feed, including validation for fake extensions. | Logged in with Buzz access | 1. Go to Buzz 2. Upload images/videos 3. Attempt fake extension (e.g. .png on non-image) | Valid media uploaded, fake extensions rejected | .webp rejected; fake extensions accepted without check | Fail | Lacks validation and support for popular formats.
4 | Admin Language Settings | Confirms that language selection is saved and functional across sessions. | Admin access | 1. Go to Admin -> Config -> Localization 2. Change language | Language reflects immediately and is saved | Language persists but only updates after refresh | Partial | Needs dynamic UI update post-change.
5 | Buzz Post Link Sharing | Tests share link creation for Buzz posts and automatic redirection via stored token. | Buzz access | 1. Share Buzz post 2. Copy/paste generated link | Link opens correct post and auto-logs user | Link is not copied to clipboard; manual copy needed | Fail | UX failure in copy mechanism; share link logic works.
6 | Org Structure CRUD | Validates CRUD operations for organization units in Admin panel. | Admin access | 1. Access Admin -> Org Structure 2. Create/Edit/Delete unit | Changes take effect and persist | All CRUD functions work; ID field ineffective | Pass | All good, but IDs and ordering are problematic.
7 | Language Package Handling | Tests admin creation of language packs via manual input or file upload. | Admin access | 1. Go to Language Packages 2. Add new language 3. Input data or upload XLIFF | Manual input and XLIFF upload supported | Manual input partly works; XLIFF upload fails | Fail | File type restrictions block workflow; symbol issues in manual entry.
8 | Leave Management | Ensures leave application, cancellation, and filtering work with correct date handling. | Leave access | 1. Apply for leave 2. Cancel 3. Filter by status | Leaves calculate correctly and reflect accurate statuses | Works as expected; minor UX improvements suggested | Pass | Add 'Show All' filter for convenience.
9 | Buzz Feed Sorting | Tests backend-driven sorting of Buzz posts by likes/comments. | Buzz access | 1. Press 'Most Liked' / 'Most Commented' | Data fetched in new order from backend | Sorting triggers API call; frontend reloads unchanged media | Pass | API exposed to users; potential optimization needed.
10 | Timesheet Entry CRUD | Ensure employees can manage daily time entries, submit, and update within timesheet module. | User has access to Timesheets | 1. Go to Timesheets 2. Add/edit/delete entries 3. Submit timesheet | All changes saved; submission confirmed; editable before approval | CRUD works well; real-time updates between screens | Pass | Token exposure not applicable; secure behavior confirmed.